| Construction Progress and Inspection Report U.S. Department of Transportation Airport Grant Program Federal Aviation Administration |  |  |  |  |  | Period Ending |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Project Number FAA AIP No. TBD SFO Contract {{ contract_number}} |
| Airport Name San Francisco International Airport (SFO) |  |  |  |  |  |  |
| Project Description {{ project_name }} |  |  |  |  | Contractor’s Name Granite Construction Company |  |
| - Contract Time {{ contract_time }} |  | No. Days Charged to Date: {{ days_charged }} | Last Working Day Charged (Date): Friday, {{ period_end }} |  |  |  |
| - Brief Weather Summary this Period, including Approximate Rainfall and Periods of Below Freezing Temperature (On earthwork jobs, include soil conditions.) {{ weather_summary }} |  |  |  |  |  |  |
| - Rough Estimate of Percent Completion to Date of Construction Phases (Include items such as clearing, grading, drainage, base, surface, lighting, etc.) {{ overall_completion_pct }} |  |  |  |  |  |  |
| - Work Completed or In Progress this Period - {{ work_summary }} |  |  |  |  |  |  |
| 5a. Summary of Laboratory and Field Testing this Period (Note failing tests and any retests. Summarize out-of-tolerance.) {{ lab_testing_summary }} |  |  |  |  |  |  |
| 5b. Material (Identify material subject to pay reduction.) {{ materials_summary }} |  |  |  |  |  |  |
| 6. Description of Anticipated Work by Contractor for Next Period # Mobilization Activities: Continue traffic control and maintain low-profile barricades, delineators, and rope lines around the work area. Continue subsurface utility investigation and potholing to verify and protect existing FAA communication and power, airfield electrical, storm drain, water, industrial waste, gas, and power lines. # Asphalt Pavement Rehabilitation: Perform saw cutting of project paving limits. Begin milling of Taxiway Z with depths ranging between four and twelve inches. Conduct post-grind survey to verify grades. # Airfield Electrical: Continue electrical demolition, including removal of lights, conduit, and signage. # 12kV Electrical Infrastructure: Excavation and installation of 12kV manhole and associated shoring boxes. Begin excavation and placement of the lower 12kV duct bank. # Environmental and Stormwater Protection: Maintain SWPPP protections, including drainage inlet mats and surface sweeping. Environmental testing was performed on five samples taken throughout the site during utility potholing investigations. PFAS was identified in 2 of the 5 samples. Handling and disposal of contaminated waste is currently being discussed with the Contractor. |  |  |  |  |  |  |
| 7. Problem Areas/Other Comments (Include revisions to plans and specifications approved or denied, delays, difficulties, etc., and actions taken.) - Bulletin Issuance: Bulletin #1 (5/19/2025): Revisions to the plans include utility lid adjustments, storm drain invert adjustment, additional storm drain details, callout references, marking details, electrical callouts, and 12kV manhole details. Bulletin #2 (7/18/2025): Revisions to the plans include the addition of addressable devices for inpavement runway guard lights, and additional elevated taxiway sign and base. Bulletin #3 (8/1/2025): Revisions to the plans include horizontal adjustment of inpavement taxiway centerline lights, 12kV grounding wire and rods. Bulletin #4 (8/15/2025): Revisions to the plans include the removal of temporary blackout striping along the centerline. - Other: Additional milling was required along the 12kV trench due to the existing pavement thickness being greater than the 3 inches shown in the plans. The extra asphalt millings removed were tracked on a Force Account basis. QA laboratory test results for the P-401 control strip did not pass. Another control strip will be placed. The 12kV duct bank alignment is under redesign to account for existing utility depths. |  |  |  |  |  |  |
| SPONSOR’S INSPECTOR OR REPRESENTATIVE |  |  |  |  |  |  |
| Date 8/27/2025 | Typed or Printed Name and Title ## Daniel Castillo, EIT, CMIT Resident Engineer |  |  | Signature |  |  |

Photos of Select Construction Activities

Figure 1: Site Limits and Traffic Control Signage for Deadhead Tug Route

Figure 2: Milling Asphalt Prior to 12kv Ductbank Excavation

Photos of Select Construction Activities

Figure 3: Installation of Drainage Inlet Mats for SWPPP

Figure 4: P-403 Asphalt Base Course Control Strip Placement