## P-610 28-Day
Sample Date | QA Lab ID. | QC Lab ID. | Supplier | Mix ID | Source of Sample | Sample | Date tested | Age (Days) | Actual QA | Actual QC | Design strength | Pass/Fail? | Slump QA | Slump QC | Slump Pass/Fail | Air Content QA | Air Content QC | Air Content Pass/Fail | Remark | Sample By | Submittal # | MIX | Manufacturer | air content
2026-03-05 | 92261 | 26-026193 | Graniterock | 572648 | PRECASTS IN THE LAY-DOWN YARD | A | 2026-03-12 | 7 |  | 3730 |  |  |  | 3.5 |  |  | 2 |  |  | QC - Ryan MacDonald | SUB 022 | T65A4M4 | Folsom RM | 5
[6 empty] | B | 2026-03-19 | 14 |  | 4620 | [10 empty] | 56 | 2019-001 | Royal | 5.4
[6 empty] | C | 2026-04-02 | 28 | 4340 | 4860 | 4000
[6 empty] | D | 2026-04-02 | 28 | 4220 | 4890 | 4000 | Pass | [8 empty] | 65 | 572648 | Graniterock | 2
2026-03-12 | 92262 | 26-029281 | Graniterock | 572648 | PRECASTS IN THE LAY DOWN YARD | A | 2026-03-19 | 7 | [5 empty] | 4 |  |  | 3.1 |  |  |  | 64R1 | 57180 | Graniterock | 2
[6 empty] | B | 2026-03-26 | 14 |  | 4760
[6 empty] | C | 2026-04-09 | 28 | 4920 | 4980 |  | Pass | [11 empty] | 5
[6 empty] | D | 2026-04-09 | 28 | 4860 | 5020 |  | Pass
2026-03-19 | 93688 | 26-032679 | GRANITE ROCK | 572648 | 520 S. AIRPORT BLVD BARD FOR WIND CONES, TRANSFORMER HOUSING, SIGN BASES | A | 2026-03-26 | 7 | 3260 | 3360 |  |  | 3.5 | 3.5 | Pass | 2.2 | 2 | PASS
[6 empty] | B | 2026-04-16 | 28 |  |  |  | Pass
[6 empty] | C | 2026-04-16 | 28 |  |  |  | Pass
2026-03-25 | 94109 | 26-035379 | GRANITE ROCK | 572648 | CONCRETE FORMS, TRANSFORMER HOUSING | A | 2026-04-01 | 7 | 3490 | 4310 |  |  | 4.25 | 4.25 | Pass | 1.2 | 2.5 | PASS
[6 empty] | B | 2026-04-08 | 14 |  | 5040
[6 empty] | C | 2026-04-22 | 28 |  |  |  | Pass
[6 empty] | D | 2026-04-22 | 28 |  |  |  | Pass
2026-04-01 | 94112 |  | Graniterock | 571801 |  | A | 2026-04-08 | 7 | 5740 | 5370 |  |  | 2.75 | 2.75 | Pass | 1.6 | 1.5 | PASS
|  | 26-038956 |  |  |  | B | 2026-04-29 | 28 |  |  |  | Pass
[6 empty] | C | 2026-04-29 | 28 |  |  |  | Pass
2026-04-03 | 94113 | 26-038956 | Graniterock | 571801 | FILLED HOLES FOR TAXIWAY H, ALL CENTERLINE + 6 EDGE LIGHTS ON NS | A | 2026-04-10 | 7 | 4590 |  |  |  | 3.5 | 3.5 | Pass | 1.7 | 1.8 | PASS
[6 empty] | B | 2026-05-01 | 28 |  |  |  | Pass
[6 empty] | C | 2026-05-01 | 28 |  |  |  | Pass
2026-04-04 | 95309 |  | Graniterock | 571801 | TAXIWAY H, FILLED HOLES FOR ALL HOLD BAR LIGHTS, 3 TRANSFORMER HOUSINGS & 4 EDGE LIGHTS | A | 2026-04-11 | 7 | 5460 |  |  |  | 4 | 4.25 | Pass | 1.2 | 1.3 | PASS
[6 empty] | B | 2026-04-11 | 7 | 5630
[6 empty] | C | 2026-05-02 | 28 |  |  |  | Pass
[6 empty] | D | 2026-05-02 | 28 |  |  |  | Pass
2026-04-06 |  |  |  |  | Canceled | A | 2026-04-06
|  | 26-040817 |  |  |  | B | 2026-04-06 |  |  |  |  | Pass
[6 empty] | C | 2026-04-06 |  |  |  |  | Pass
2026-04-07 | 94218 |  | Graniterock | 571801 | Conduit connecting lights ABCD on 1LW1 & filled holes where TLC1-16-6A, TLC1-16-6B, TLC1-16-6C, TLC1-16-8, C14-1, and 1LH2 were demoed | A | 2026-04-07 | [5 empty] | 4.5 | 4 | Pass | 1.6 | 1.3 | PASS
|  | 26-041387 |  |  |  | B | 2026-04-07 |  |  |  |  | Pass
[6 empty] | C | 2026-04-07 |  |  |  |  | Pass
2026-04-08 |  |  | Graniterock | 572648 | 5kV duct bank 20 to 40 ft north of sectional D7 | A | 2026-04-15 | 7 | [5 empty] | 3.5 |  |  | 1.4
|  | 26-042282 |  |  |  | B | 2026-05-06 | 28 |  |  |  | Pass
[6 empty] | C | 2026-05-06 | 28 |  |  |  | Pass
2026-04-08 |  |  | Graniterock | 571801 | 1LW1 cans ABCD, 1LW2 cans ABC, conduit between 1LW3 ABC, and conduit between W4 cans AB | A | 2026-04-08 | [6 empty] | 4 |  |  | 1.4
|  | 26-042644 |  |  |  | B | 2026-04-08 |  |  |  |  | Pass
[6 empty] | C | 2026-04-08 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
[6 empty] | A | 0
[6 empty] | B | 0 |  |  |  |  | Pass
[6 empty] | C | 0 |  |  |  |  | Pass
Formulas:
Date tested = [Sample Date]+[Age (Days)]
Date tested = [Sample Date, row above]+[Age (Days)]

## P-610 HES
Sample Date | QA Lab ID. | QC Lab ID. | Truck Ticket | Supplier | Mix ID | Source of Sample | Sample | Date tested | Age (Days) | Actual QA | Actual QC | Design strength | Pass/Fail? | Spread QA | Spread QC | Slump Pass/Fail | Air Content QA | Air Content QC | Air Content Pass/Fail | Remark | Sample By |  | CENTRAL
[7 empty] | A | 1900-01-06 | 7 | [11 empty] | QC - Ryan MacDonald | GRANITE ROCK | 3EFE75Q1
[7 empty] | B | 1900-01-13 | 14 |  |  | 4000 | Pass | [8 empty] | Central
[7 empty] | C | 1900-01-27 | 28 |  |  | 4000 | Pass | [8 empty] | GRC
[7 empty] | A | 1900-01-06 | 7 | [12 empty] | Royal
[7 empty] | B | 1900-01-27 | 28 |  |  |  | Pass | [8 empty] | Cemex
[7 empty] | C | 1900-01-27 | 28 |  |  |  | Pass | [8 empty] | HES
[7 empty] | A | 1900-01-06 | 7
[7 empty] | B | 1900-01-27 | 28 |  |  |  | Pass
[7 empty] | C | 1900-01-27 | 28 |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
[7 empty] | A | 0
[7 empty] | B | 0 |  |  |  |  | Pass
[7 empty] | C | 0 |  |  |  |  | Pass
Formulas:
Date tested = [Sample Date]+[Age (Days)]
Date tested = [Sample Date, row above]+[Age (Days)]

## Concrete schedule
Schedule pour date | Supplier | Mix ID | Cubic Yard poured | Received concrete tags? | Status | 1st break (1day or 3days) | Received QA test results? Yes or No | 7 days breaks | Received QA test results? Yes or No | 28 days breaks | Received QA test results? Yes or No | 56 days breaks | Received QA test results? Yes or No |  |  |  | Central | Poured
2024-01-25 | Central | 3EFE75Q1 | 63 | Yes | Poured | 2024-02-01 | Yes |  |  | 2024-02-22 | Yes | 2024-03-21 |  | 571852 | GRC | Yes | Folsom | Canceled
2024-01-26 | Central | 3EFE75Q1 | 54 | Yes | Poured | 2024-02-02 | Yes |  |  | 2024-02-23 | Yes | 2024-03-22 |  | X7BCC5P1 | CENTRAL | No | GRC
2024-01-27 | Central | 3EFE75Q1 | 72 | Yes | Poured | 2024-02-03 | Yes |  |  | 2024-02-24 | Yes | 2024-03-23 |  | 3EFE75Q1 | CENTRAL |  | Royal
2024-01-29 | Central | 3EFE75Q1 | 72 | Yes | Poured | 2024-02-05 | Yes |  |  | 2024-02-26 | Yes | 2024-03-25 |  |  |  |  | Cemex
2024-01-30 | Central | 3EFE75Q1 | 63 | Yes | Poured | 2024-02-06 | Yes |  |  | 2024-02-27 | Yes | 2024-03-26 |  |  |  |  | HES
2024-01-31 |  |  |  |  | Canceled | [11 empty] | CLMS
2024-02-01 |  |  |  |  | Canceled
2024-02-02 | Central | 3EFE75Q1 | 18 | Yes | Poured | 2024-02-09 | Yes | 2024-02-09 | Yes | 2024-03-01 | Yes
2024-02-03 | Central | 3EFE75Q1 | 99 | Yes | Poured | 2024-02-12 | Yes |  |  | 2024-03-04 | Yes | 2024-03-30
2024-02-05 | Central | 3EFE75Q1 | 27 | Yes | Poured | 2024-02-12 | Yes |  |  | 2024-03-04 | Yes | 2024-04-01
2024-02-06 | Central | 3EFE75Q1 | 7 | No | Poured | 2024-02-13 | Yes |  |  | 2024-03-05 | Yes | 2024-04-02
2024-02-07 |  |  |  |  | Canceled
2024-02-08 | Central | 3EFE75Q1 | 63 | Yes | Poured | 2024-02-14 | Yes | 2024-02-15 |  | 2024-03-07 | No | 2024-04-04
2024-02-09 | Central | X7BCC5P1 | 9 | Yes | Poured | 2024-02-14 | Yes | 2024-02-16 |  | 2024-03-08 | Yes | 2024-04-05
2024-02-09 | Central | 3EFE75Q1 | 9 | Yes | Poured | 2024-02-14 | Yes |  |  | 2024-03-08 | No
2024-02-10 | Central | 3EFE75Q1 | 9 | Yes | Poured | 2024-02-13 | No | 2024-02-19 | No | 2024-03-11 | No | 2024-04-08 | No
2024-02-12 | Central | 3EFE75Q1 | 18 | Yes | Poured | 2024-02-15 | Yes |  |  | 2024-03-11 | No | 2024-04-08
2024-02-13 | GRC | 571852 | 36 | Yes | Poured | 2024-02-14 | Yes |  |  | 2024-03-12 |  | 2024-04-09
2024-02-14 | Central | 400FLO | 30 | Yes | Poured |  |  |  |  | 2024-03-13 |  | 2024-04-10
2024-02-15 | Central | 3EFE75Q1 | 72 | Yes | Poured | 2024-02-19 | Yes | 2024-02-22 |  | 2024-03-14 |  | 2024-04-11
2024-02-16 | Central | 3EFE75Q1 | 14 | Yes | Poured | 2024-02-19 | Yes | 2024-02-23 |  | 2024-03-15 |  | 2024-04-12
2024-02-17 |  |  |  |  | Canceled |  | Yes
2024-02-19 |  |  |  |  | Canceled |  | Yes |  |  | 2024-03-20 |  | 2024-04-17
2024-02-20 |  |  |  |  | Canceled |  | Yes
2024-02-21 |  |  |  |  | Canceled |  | Yes
2024-02-22 |  |  |  |  | Canceled |  | Yes
2024-02-23 |  |  |  |  | Canceled |  | Yes
2024-02-24 | Central | 3EFE75Q1 | 18 | Yes | Poured | 2024-02-28 | Yes |  |  | 2024-03-25
2024-02-24 | Central | 3E0EG9C1 | 36 | Yes | Poured | 2024-02-28 | Yes | 2024-03-04 | No | 2024-03-23 | Yes
2024-02-26 | Central | 3EFE75Q1 | 27 | Yes | Poured | 2024-02-29 | Yes |  |  | 2024-03-25
2024-02-27 | Central | 3EFE75Q1 | 63 | Yes | Poured | 2024-03-01 | Yes |  |  | 2024-03-26
2024-02-28 | Central | 3EFE75Q1 | 90 | Yes | Poured | 2024-03-02 | Yes |  |  | 2024-03-27
2024-02-29 | GRC | 571852 | 27 | Yes | Poured | 2024-03-01 | Yes |  |  | 2024-03-28
2024-03-01 | Central | 3EFE75Q1 |  |  | Canceled
2024-03-02 | Central | 3EFE75Q1 |  |  | Canceled
2024-03-04 | Central | 3E0EG9C1 | 41.5 | Yes | Poured |  |  | 2024-03-11 | Yes | 2024-04-01
2024-03-04 | Central | 3EFE75Q1 | 5 | Yes | Poured |  |  | 2024-03-11 | No | 2024-04-01
2024-03-05 |  | 3EFE75Q1 |  | No | Canceled
2024-03-06 |  | 3EFE75Q1 |  |  | Canceled
2024-03-07 | Central | 3EFE75Q1 | 5 | Yes | Poured |  |  | 2024-03-13 | Yes | 2024-04-04
2024-03-08 |  |  |  | No | Canceled
2024-03-09 |  |  |  | No | Canceled
2024-03-11 | Central | S18100EX | 72 | Yes | Poured |  |  |  |  | 2024-04-08
2024-03-13 | GRC | 571957S5 | 2 | Yes | Poured | 2024-03-14 | No |  |  | 2024-04-10
2024-03-16 |  |  |  | No | Canceled
2024-03-18 | Central | 3E0EG9C1 | 43 | Yes | Poured |  |  | 2024-03-25 |  | 2024-04-15
2024-03-18 | Central | S18100EX |  | Yes | Poured
2024-03-19 |  |  |  | No | Poured
2024-03-20 | Central | X7BCC5P1 | 2 | No | Poured
2024-03-21 | Central | X7BCC5P1 | 9 | Yes | Poured
2024-03-22 | Central | X7BCC5P1 | 27 | Yes | Poured
2024-03-23 |  | 3EFE75Q1 | 36 | Yes | Poured
2024-03-23 |  | 3EFE75Q1 | 3 | Yes | Poured
2024-03-25 | Central | 4E5EC5E1 | 25 | Yes | Poured
2024-03-26 | GRC
2024-03-26 |  | X7BCC5P1
2024-03-27 |  | X7BCC5P1
2024-03-28 |  | X7BCC5P1
2024-03-29 |  | X7BCC5P1
2024-03-30 |  | X7BCC5P1
1047.5
Formulas:
Schedule pour date = [Schedule pour date, row above]+1

## Failing Concrete
Source of Sample | Sample Date | Report No. | Supplier | Mix ID | Batch Size (CY) | Sample | Date tested | Age (Days) | Actual | Design Age | Design strength | Pass/Fail? | Remark
Site Work - FAA-Line East of C7 | 2024-02-09 | 24-HAY-00250 | Central | X7BCC5P1 | 9 | A | 2024-02-14 | 5 | 2790 | 3 | 4000 | Fail | Fail to the design strength is 4000 psi @ 72hr
[6 empty] | B | 2024-03-08 | 28 | 5290 |  | 4000 | Pass
[6 empty] | C | 2024-03-08 | 28 | 5300 |  | 4000 | Pass
x
x
x